## 00_README
Progression Checklist Workbook
Version | v1.0.2
Purpose | Detailed Excel checklist to drive the project from current state to production without AI deviation.
Current Position | Controlled Execution / Gate 4 preparation
Current Priority | Close Gate 4: seed-manifest-only execution, standardized result pack, explicit failure reasons, resume-safe restart with same outdir.
Usage | Update 03_DETAILED_CHECKLIST first. Then review 01_OVERVIEW, 04_CURRENT_PRIORITY, and 06_HANDOFF_TEMPLATE before changing chat.
Production Rule | Production is closed only when critical gates are closed with evidence, registry + runtime layers are operational, and Phase 9 readiness review passes.
Primary Repo | https://github.com/tiumbj/Bot_Data_Basese
Uploaded Source Files | PROJECT_PROGRESSION_CHECKLIST.txt; Master Mapping Intelligent Data Base Production_v1_2_0.txt; project conversation.txt
Operator Rules
[ ] | Always identify the gate before starting work.
[ ] | If the task does not move one OPEN gate closer to CLOSED, do not start it.
[ ] | Do not confuse logs/specs/plans with runtime truth.
[ ] | Do not reduce scope or skip locked TF coverage.
[ ] | Do not rewrite the system before current gate closure requires it.

## 01_OVERVIEW
CURRENT POSITION | Controlled Execution / Gate 4 preparation
CURRENT GATE | Gate 4 - Execution Evidence
CURRENT LAYER | Research Evidence / Execution Evidence
CURRENT PRIORITY | Resume-safe runner + standardized result pack + explicit failure reasons + same-outdir restart recovery
LOCKED SEQUENCE | Truth Gate -> Seed Manifest -> Controlled Execution -> Standardized Result Pack -> Candidate Registry Publish -> Feature/Label Runtime -> Intelligent DB -> Downstream Bot / MT5
ARCHITECTURE DIRECTION | Parquet + Zstd, Polars Lazy scan_parquet(), Arrow/NumPy-friendly path, custom Numba kernel, separated orchestration, future Ray/Optuna later.
NOT CURRENT NEXT ACTION | Do not rewrite the whole system around Ray now. Do not introduce Optuna as the main task now. Do not treat architecture work as production closure.
DECISION RULE | If a proposed task does not move one OPEN gate closer to CLOSED, it is architecture research only, not the current production priority.
PHASE STATUS GUIDE
Phase 0 - Concept Lock | Mostly closed
Phase 1 - Canonical Data Ready | In progress
Phase 2 - Research Evidence Truth | In progress
Phase 3 - Seed Manifest Gate | In progress
Phase 4 - Execution Evidence Gate | Current blocker / in progress
Phase 5 - Registry Publish Gate | Open
Phase 6 - Feature / Label / Regime Runtime | Open
Phase 7 - Intelligent DB Runtime | Open
Phase 8 - Downstream Bot / MT5 Integration | Open
Phase 9 - Production Closure & Weekly Loop | Open

## 02_PHASE_GATES
Gate | Phase | Pass Only If | Current State | Why It Matters | Evidence Required | Immediate Next Move | Not Allowed
Gate 1 | Canonical Data Ready | All locked TF datasets exist; integrity checks pass; source/version recorded | IN_PROGRESS | All downstream layers must read one trusted market-data spine | Integrity report; version manifest; TF coverage inventory | Finish integrity automation and provenance snapshots | Do not assume data existence equals data truth
Gate 2 | Research Evidence Truth | Coverage matrix, micro-exit coverage, kill-stage summary, standardized metrics pack, explicit recommendation | IN_PROGRESS | Transforms research quantity into machine-readable evidence truth | Coverage artifacts; metrics pack; recommendation table | Standardize evidence pack and recommendation contract | Do not move to execution from ad hoc logs
Gate 3 | Seed Manifest Gate | CSV + JSONL manifest exist; blocked rows excluded; eligible TF explicit; recommendation allows seed full-run | IN_PROGRESS | Limits execution to truth-gated candidates | Manifest files; schema validation; exclusion log | Finalize manifest contract and execution-only input path | Do not run full universe directly
Gate 4 | Execution Evidence Gate | Seed-manifest-only execution; standardized result pack; explicit fail reasons; resume-safe restart; idempotent recovery | IN_PROGRESS | Current blocker between controlled runs and production-safe execution | Acceptance test report; recovery metrics; result pack schema | Promote one runner and pass kill/restart test | Do not use new outdir-per-retry as promoted recovery model
Gate 5 | Registry Publish Gate | Auto-publish candidate registry; central approval rules; approved-only package build | OPEN | Separates raw execution results from approved truth | Registry publish log; approval policy; package manifest | Build candidate registry promotion flow | Do not let downstream read raw candidates
Gate 6 | Feature/Label/Regime Runtime | Shared features/labels/regimes are reproducible, queryable, and versioned | OPEN | Required for intelligent database runtime and traceable analytics | Feature cache build; schema lock; label/regime runtime reports | Implement build_base_feature_cache and schema lock | Do not substitute backtest outputs for feature runtime
Gate 7 | Intelligent DB Runtime | Unified ingestion; same retrieval truth for human and bot; feedback linkage | OPEN | Centralizes intelligence retrieval and closes source-to-outcome loop | Ingestion report; retrieval contract; feedback linkage test | Build ingestion and retrieval contract | Do not split truth across client-specific stores

## 03_DETAILED_CHECKLIST
Workbook Metrics |  |  | Phase Summary | [7 empty] | Editing Instructions
Task table starts at row | 20 |  | Phase | Tasks | Done | In Progress | Open | Blocked | Progress % |  | Edit only blue cells: Status, Owner, Target Date, Notes.
Total Tasks | 79 |  | Phase 0 | 6 | 6 | 0 | 0 | 0 | 100% |  | Use statuses: DONE, IN_PROGRESS, OPEN, BLOCKED, NOT_STARTED.
Done | 7 |  | Phase 1 | 8 | 1 | 2 | 5 | 0 | 12.5% |  | Keep Source explicit with file names and URLs.
In Progress | 10 |  | Phase 2 | 8 | 0 | 4 | 4 | 0 | 0% |  | Add evidence rows in 07_EVIDENCE_LOG whenever a gate moves.
Open / Not Started | 62 |  | Phase 3 | 6 | 0 | 2 | 4 | 0 | 0%
Blocked | 0 |  | Phase 4 | 12 | 0 | 2 | 10 | 0 | 0%
Overall Progress % | 8.861% |  | Phase 5 | 7 | 0 | 0 | 7 | 0 | 0%
|  |  | Phase 6 | 8 | 0 | 0 | 8 | 0 | 0%
|  |  | Phase 7 | 8 | 0 | 0 | 8 | 0 | 0%
|  |  | Phase 8 | 8 | 0 | 0 | 8 | 0 | 0%
|  |  | Phase 9 | 8 | 0 | 0 | 8 | 0 | 0%
ID | Phase | Gate | Layer | Workstream | Task | Why | Exit Criteria | Evidence Artifact | Status | Priority | Current Blocker | Allowed Next Step | Not Allowed | Source | Owner | Target Date | Notes | DoneFlag | InProgFlag | OpenFlag | BlockedFlag
1 | Phase 0 | Foundation | Governance | Project Truth | Lock research timeframe universe (M1,M2,M3,M4,M5,M6,M10,M15,M30,H1,H4,D1) | Prevent selective TF drift and incomplete coverage | Locked TF list referenced in all planning and runners | Mapping files + checklist | DONE | High | None | Use locked TF list in research/evidence gates | Do not narrow TF scope for convenience | uploaded: PROJECT_PROGRESSION_CHECKLIST.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 1 | 0 | 0 | 0
2 | Phase 0 | Foundation | Governance | Project Truth | Separate research timeframe scope from execution timeframe scope | Avoid conflating research coverage with live execution cadence | Both scopes documented and referenced independently | Checklist + architecture notes | DONE | High | None | Keep research coverage broad while live execution remains selective | Do not claim production readiness from research TF only | uploaded: PROJECT_PROGRESSION_CHECKLIST.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 1 | 0 | 0 | 0
3 | Phase 0 | Foundation | Governance | Project Truth | Lock micro exit as mandatory base layer | Ensure exit logic is part of truth, not optional add-on | Every research/evidence phase references micro exit requirement | Mapping + checklist | DONE | High | None | Retain micro exit in all future candidate evaluation | Do not bypass micro exit to speed exploration | uploaded: PROJECT_PROGRESSION_CHECKLIST.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 1 | 0 | 0 | 0
4 | Phase 0 | Foundation | Governance | Project Truth | Lock custom controllable backtest core as target direction | Preserve path-dependent execution control | Architecture direction and checklist both reference custom core | Checklist + source register | DONE | High | None | Use custom controllable engine direction | Do not treat VectorBT as production core | uploaded: PROJECT_PROGRESSION_CHECKLIST.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 1 | 0 | 0 | 0
5 | Phase 0 | Foundation | Governance | Project Truth | Lock intelligent database as central system of truth | Ensure bot runtime is a client of central truth, not standalone truth generator | Central truth model repeated in planning artifacts | Checklist + source register | DONE | High | None | Design downstream layers as clients of central truth | Do not let bot create truth outside central DB | uploaded: PROJECT_PROGRESSION_CHECKLIST.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 1 | 0 | 0 | 0
6 | Phase 0 | Foundation | Governance | Governance | Define runner classes: preflight / execution / legacy | Reduce ambiguity between orchestration and production evidence | Runner class rubric documented and used in planning | Checklist | DONE | High | None | Tag runners before use | Do not run untagged runners | uploaded: PROJECT_PROGRESSION_CHECKLIST.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 1 | 0 | 0 | 0
7 | Phase 1 | Gate 1 | Data Foundation | Canonical Data | Create single canonical source path for all consumers | Prevent divergent datasets across research/labels/bot | One canonical path documented and used | Bootstrap config + source register | DONE | High | None | Use canonical path in all downstream tools | Do not fork dataset roots ad hoc | uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 1 | 0 | 0 | 0
8 | Phase 1 | Gate 1 | Data Foundation | Canonical Data | Build multitimeframe dataset for all locked TF | Research truth requires complete TF universe | All locked TF datasets exist | Dataset build report | IN_PROGRESS | High | Coverage incomplete / not fully evidenced | Complete missing TF builds and verify outputs | Do not skip inconvenient TF | uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 1 | 0 | 0
9 | Phase 1 | Gate 1 | Data Foundation | Canonical Data | Build parquet cache for all TF | Enable scalable repeated access | Parquet cache exists for all locked TF | Parquet cache inventory | IN_PROGRESS | High | Operational evidence incomplete | Finish cache coverage and inventory | Do not rely on scattered raw files only | uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 1 | 0 | 0
10 | Phase 1 | Gate 1 | Data Foundation | Canonical Data | Record dataset version/provenance per build | Make outputs reproducible | Each dataset build has timestamp/version/source metadata | Version manifest | OPEN | High | Provenance flow not fully operational | Add version snapshot manifest | Do not overwrite data without provenance | uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
11 | Phase 1 | Gate 1 | Data Foundation | Canonical Data | Automate integrity checks (row counts, schema, gaps, duplicates) | Turn data availability into data truth | Integrity suite runs and passes across all locked TF | Integrity report | OPEN | High | Automation gap | Implement and store integrity report | Do not assume existence = integrity | uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
12 | Phase 1 | Gate 1 | Data Foundation | Canonical Data | Validate timezone/session normalization | Avoid hidden inconsistencies in intraday logic | Timezone/session rules documented and tested | Normalization test report | OPEN | Medium | Need explicit tests | Create session normalization tests | Do not mix sessions silently | uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
13 | Phase 1 | Gate 1 | Data Foundation | Canonical Data | Create reproducible research snapshots | Allow any research run to be reproduced later | Snapshot manifest can recreate dataset state used by a run | Snapshot manifest | OPEN | High | Snapshot process missing | Add snapshot write/read workflow | Do not claim reproducibility without snapshot | uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
14 | Phase 1 | Gate 1 | Data Foundation | Canonical Data | Define cleanup/retention rules for storage-heavy runs | Keep HPC experimentation from exhausting storage | Retention policy documented and applied | Ops retention note | OPEN | Medium | No cleanup policy | Add retention schedule and archive rules | Do not scale heavy runs without cleanup plan | uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
15 | Phase 2 | Gate 2 | Research Evidence | Evidence Truth | Generate coverage_by_timeframe across locked TF | Need explicit coverage truth by TF | Coverage matrix exists and is current | coverage_by_timeframe artifact | IN_PROGRESS | High | Standardization incomplete | Regenerate and freeze coverage matrix | Do not infer coverage from ad hoc logs | uploaded: project conversation.txt; uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 1 | 0 | 0
16 | Phase 2 | Gate 2 | Research Evidence | Evidence Truth | Generate micro_exit_coverage_matrix | Need evidence that mandatory micro exit was tested | Matrix exists for every locked TF | micro_exit_coverage_matrix artifact | IN_PROGRESS | High | Standardization incomplete | Generate matrix with locked TF coverage | Do not mark micro exit as covered without artifact | uploaded: project conversation.txt; uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 1 | 0 | 0
17 | Phase 2 | Gate 2 | Research Evidence | Evidence Truth | Generate kill_stage_summary | Need to know where candidates fail | Kill stage summary stored and readable | kill_stage_summary artifact | IN_PROGRESS | High | Pipeline not fully standardized | Add standardized kill-stage output | Do not rely on memory or chat summary | uploaded: project conversation.txt; uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 1 | 0 | 0
18 | Phase 2 | Gate 2 | Research Evidence | Evidence Truth | Generate standardized_metrics_pack | Convert runs into comparable evidence | Metrics pack contains required KPIs and consistent schema | standardized_metrics_pack | OPEN | High | Output standard not fully locked | Finalize schema and export pipeline | Do not compare candidates with incompatible metric shapes | uploaded: project conversation.txt; uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
19 | Phase 2 | Gate 2 | Research Evidence | Evidence Truth | Write explicit recommendation per candidate / TF | Need machine-readable next-step truth | Recommendation field exists and is explicit | Recommendation table | OPEN | High | Recommendation logic incomplete | Create explicit recommendation column | Do not promote ambiguous candidates | uploaded: project conversation.txt; uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
20 | Phase 2 | Gate 2 | Research Evidence | Evidence Truth | Integrate OOS / walk-forward evidence into same truth pack | Production candidates need more than in-sample wins | OOS/WF metrics included in standardized pack | Extended metrics pack | OPEN | High | Integration gap | Add OOS/WF fields to evidence pack | Do not call a candidate robust from IS only | uploaded: project conversation.txt; uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
21 | Phase 2 | Gate 2 | Research Evidence | Evidence Truth | Track reject reasons with normalized codes | Reduce ambiguity in failure analysis | Reject reason taxonomy is stored consistently | Reject reason dictionary | OPEN | Medium | Taxonomy incomplete | Normalize reject codes | Do not bury reject logic in free text only | uploaded: project conversation.txt; uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
22 | Phase 2 | Gate 2 | Research Evidence | Evidence Truth | Freeze truth gate decision contract | Need stable handoff to seed manifest | Truth gate emits deterministic decisions | Truth gate contract doc + artifact | IN_PROGRESS | High | Some fields still evolving | Freeze contract and validate sample outputs | Do not move to execution without stable gate fields | uploaded: project conversation.txt; uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 1 | 0 | 0
23 | Phase 3 | Gate 3 | Execution Handoff | Seed Manifest | Create truth_gate_seed_manifest.csv | Execution must use gated seed set | CSV manifest exists and is current | truth_gate_seed_manifest.csv | IN_PROGRESS | High | Need final promoted artifact | Generate latest CSV from truth gate | Do not launch blind full-universe execution | uploaded: project conversation.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 1 | 0 | 0
24 | Phase 3 | Gate 3 | Execution Handoff | Seed Manifest | Create truth_gate_seed_manifest.jsonl | Need execution-friendly row-level input | JSONL manifest exists and matches CSV | truth_gate_seed_manifest.jsonl | IN_PROGRESS | High | Need final promoted artifact | Generate JSONL alongside CSV | Do not maintain only manual lists | uploaded: project conversation.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 1 | 0 | 0
25 | Phase 3 | Gate 3 | Execution Handoff | Seed Manifest | Exclude blocked killer-layer rows | Prevent known-bad candidates from wasting compute | Blocked rows absent from seed manifest | Manifest validation log | OPEN | High | Validation not formalized | Add block/exclusion validation | Do not send blocked rows into execution | uploaded: project conversation.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
26 | Phase 3 | Gate 3 | Execution Handoff | Seed Manifest | Record eligible TF explicitly in manifest | Ensure TF handoff is deterministic | Eligible TF field populated for each row | Manifest schema check | OPEN | High | Field enforcement incomplete | Add explicit eligible_TF field | Do not infer TF eligibility externally | uploaded: project conversation.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
27 | Phase 3 | Gate 3 | Execution Handoff | Seed Manifest | Attach recommendation = ALLOW_VT_FULL_RUN_ON_SEED_SET | Need machine-readable handoff decision | Recommendation string present and validated | Manifest validation output | OPEN | High | Recommendation lock incomplete | Finalize recommendation emission | Do not use manifest rows without recommendation | uploaded: project conversation.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
28 | Phase 3 | Gate 3 | Execution Handoff | Seed Manifest | Validate execution reads seed manifest only | Close the gate between research truth and execution truth | Execution runner input contract points only to seed manifest | Execution preflight log | OPEN | High | Runner input contract incomplete | Wire runner to manifest-only mode | Do not run full universe directly | uploaded: project conversation.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
29 | Phase 4 | Gate 4 | Execution Evidence | Execution Runner | Promote one execution runner as the controlled path | Need one operational spine for Gate 4 | Runner selected, tagged, and documented | Promoted runner note | IN_PROGRESS | High | Historical runner drift | Freeze one promoted runner path | Do not juggle multiple equal 'production' runners | uploaded: project conversation.txt; uploaded: PROJECT_PROGRESSION_CHECKLIST.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 1 | 0 | 0
30 | Phase 4 | Gate 4 | Execution Evidence | Execution Runner | Run controlled seed execution only | Ensure compute is spent on truth-approved rows | Execution logs show seed-manifest-only input | Run logs + manifest reference | IN_PROGRESS | High | Need final enforcement | Keep execution scoped to seed set | Do not revert to full-universe run | uploaded: project conversation.txt; uploaded: PROJECT_PROGRESSION_CHECKLIST.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 1 | 0 | 0
31 | Phase 4 | Gate 4 | Execution Evidence | Execution Runner | Create standardized result pack per run | Need deterministic downstream consumption | Result pack schema exists and is emitted every run | standardized_result_pack | OPEN | High | Schema/output gap | Finalize pack schema and generation | Do not treat raw mixed files as final outputs | uploaded: project conversation.txt; uploaded: PROJECT_PROGRESSION_CHECKLIST.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
32 | Phase 4 | Gate 4 | Execution Evidence | Execution Runner | Emit explicit reject/error/missing-feature reasons | Need debuggable truth, not silent fail | Each failed/blocked row has reason code and message | Failure reason log | OPEN | High | Reason emission incomplete | Add explicit failure taxonomy to outputs | Do not leave blank error contexts | uploaded: project conversation.txt; uploaded: PROJECT_PROGRESSION_CHECKLIST.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
33 | Phase 4 | Gate 4 | Execution Evidence | Execution Runner | Support same-outdir restart after kill/shutdown | Core production execution requirement | Restart with same outdir resumes instead of resetting | Acceptance test evidence | OPEN | Critical | Resume-safe gap | Implement stateful resume path | Do not use new outdir per retry as promoted model | uploaded: project conversation.txt; uploaded: PROJECT_PROGRESSION_CHECKLIST.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
34 | Phase 4 | Gate 4 | Execution Evidence | Execution Runner | Skip completed jobs/groups on restart | Prevent duplicate compute and duplicate outputs | Completed rows are skipped automatically | Recovery metrics + logs | OPEN | Critical | Resume-safe gap | Persist completion state and skip logic | Do not recompute completed work | uploaded: project conversation.txt; uploaded: PROJECT_PROGRESSION_CHECKLIST.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
35 | Phase 4 | Gate 4 | Execution Evidence | Execution Runner | Prevent duplicate result rows on recovery | Need deterministic downstream packs | No duplicate rows after kill/restart test | Duplicate-check report | OPEN | Critical | Resume-safe gap | Enforce idempotent write model | Do not merge duplicate attempts manually | uploaded: project conversation.txt; uploaded: PROJECT_PROGRESSION_CHECKLIST.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
36 | Phase 4 | Gate 4 | Execution Evidence | Execution Runner | Reconstruct progress after restart | Need observability and operator trust | Progress metrics remain accurate after restart | Recovery progress report | OPEN | High | Recovery observability missing | Add restart-aware progress reconstruction | Do not reset counters silently | uploaded: project conversation.txt; uploaded: PROJECT_PROGRESSION_CHECKLIST.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
37 | Phase 4 | Gate 4 | Execution Evidence | Execution Runner | Expose recovery metrics (resumed, skipped, status) | Need visible recovery truth | Recovery metrics written per run | Recovery metrics artifact | OPEN | High | Metrics missing | Emit resumed/skipped/recovery status fields | Do not hide recovery behavior | uploaded: project conversation.txt; uploaded: PROJECT_PROGRESSION_CHECKLIST.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
38 | Phase 4 | Gate 4 | Execution Evidence | Execution Runner | Pass 5-step acceptance test (run, partial progress, kill, restart, verify) | Prove resume-safe behavior empirically | Acceptance test passes end-to-end | Acceptance test report | OPEN | Critical | Acceptance test open | Run formal test and store evidence | Do not claim production-safe before test passes | uploaded: project conversation.txt; uploaded: PROJECT_PROGRESSION_CHECKLIST.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
39 | Phase 4 | Gate 4 | Execution Evidence | Execution Runner | Separate orchestration logs from execution truth outputs | Avoid mixing monitoring with production claims | Logs and result packs have distinct paths/contracts | Path contract note | OPEN | Medium | Path hygiene issue | Define separate paths/contracts | Do not equate logs with result packs | uploaded: project conversation.txt; uploaded: PROJECT_PROGRESSION_CHECKLIST.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
40 | Phase 4 | Gate 4 | Execution Evidence | Execution Runner | Document runner class, input truth, output truth, allowed next step | Reduce AI/operator deviation | Runner metadata available before each run | Runner card | OPEN | Medium | Governance gap | Create runner metadata template | Do not start runs without runner card | uploaded: project conversation.txt; uploaded: PROJECT_PROGRESSION_CHECKLIST.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
41 | Phase 5 | Gate 5 | Registry | Registry | Create candidate registry auto-publish path from result pack | Need formal promotion from execution evidence | Candidates auto-written to registry staging | Registry publish log | OPEN | High | Publish automation missing | Map standardized pack to candidate registry | Do not hand-copy winners into registry | uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
42 | Phase 5 | Gate 5 | Registry | Registry | Define approval rules centrally | Need one policy for promotion/demotion | Approval rules encoded and versioned | Approval policy artifact | OPEN | High | Central policy gap | Write centralized approval logic | Do not approve manually in scattered scripts | uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
43 | Phase 5 | Gate 5 | Registry | Registry | Define deprecated path for invalid/outdated candidates | Need lifecycle completeness | Deprecated registry path exists | Registry lifecycle note | OPEN | Medium | Lifecycle incomplete | Add deprecation flow | Do not leave dead candidates active indefinitely | uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
44 | Phase 5 | Gate 5 | Registry | Registry | Build approved package manifest from registry | Downstream must consume approved truth only | Approved package manifest builds successfully | approved_package_manifest | OPEN | High | Publish flow missing | Build manifest generator | Do not let downstream read raw candidate pool | uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
45 | Phase 5 | Gate 5 | Registry | Registry | Version candidate and approved packages | Need reproducibility and rollback | Package version fields populated | Package version inventory | OPEN | Medium | Versioning missing | Add version metadata | Do not overwrite registry packages silently | uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
46 | Phase 5 | Gate 5 | Registry | Registry | Attach evidence lineage back to result pack and dataset snapshot | Need traceability from approved truth to source truth | Lineage fields populated in registry | Registry lineage check | OPEN | High | Lineage incomplete | Store source run + dataset snapshot IDs | Do not break traceability | uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
47 | Phase 5 | Gate 5 | Registry | Registry | Validate downstream consumes approved-only packages | Enforce central truth contract | Consumer integration test passes | Consumer test report | OPEN | High | Consumer gate open | Switch downstream readers to approved package only | Do not read raw exploratory results | uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
48 | Phase 6 | Gate 6 | Feature/Label Runtime | Feature Runtime | Implement build_base_feature_cache end-to-end | Shared features are a known major gap | Base feature cache builds from canonical data | Feature cache build report | OPEN | Critical | Known feature-layer gap | Implement and validate feature cache | Do not assume backtest outputs replace features | uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
49 | Phase 6 | Gate 6 | Feature/Label Runtime | Feature Runtime | Lock operational feature schema | Need stable contract for DB/runtime consumers | Feature schema versioned and enforced | Feature schema file | OPEN | High | Schema lock missing | Freeze schema and validation | Do not let feature columns drift silently | uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
50 | Phase 6 | Gate 6 | Feature/Label Runtime | Feature Runtime | Generate reproducible trade outcome labels | Need supervised/runtime truth tied to trades | Outcome labels can be rebuilt deterministically | Label build report | OPEN | High | Label runtime missing | Implement label generation pipeline | Do not derive labels ad hoc | uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
51 | Phase 6 | Gate 6 | Feature/Label Runtime | Feature Runtime | Generate reproducible regime labels | Need market context for retrieval and ranking | Regime labels can be rebuilt deterministically | Regime build report | OPEN | High | Regime runtime missing | Implement regime labeling pipeline | Do not assign regimes manually only | uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
52 | Phase 6 | Gate 6 | Feature/Label Runtime | Feature Runtime | Store feature/label lineage to canonical snapshot | Need reproducibility and debugging | Lineage fields include source snapshot/version | Lineage validation report | OPEN | Medium | Lineage gap | Attach snapshot metadata | Do not orphan features from source data | uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
53 | Phase 6 | Gate 6 | Feature/Label Runtime | Feature Runtime | Create query contract for feature store | Prepare intelligent DB runtime | Feature query API/schema documented | Feature query contract | OPEN | Medium | Query contract missing | Define query interface | Do not let each consumer read raw files differently | uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
54 | Phase 6 | Gate 6 | Feature/Label Runtime | Feature Runtime | Create query contract for label store | Prepare intelligent DB runtime | Label query API/schema documented | Label query contract | OPEN | Medium | Query contract missing | Define label interface | Do not mix label logic into every client | uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
55 | Phase 6 | Gate 6 | Feature/Label Runtime | Feature Runtime | Schedule recurring rebuild/update cadence | Move from ad hoc to runtime service | Rebuild cadence documented and runnable | Ops schedule note | OPEN | Medium | No recurring runtime schedule | Define scheduled rebuild/update process | Do not rely on manual refresh only | uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
56 | Phase 7 | Gate 7 | Intelligent Database | Intelligent DB | Design ingestion pipeline from registry + features + labels | Need one runtime knowledge spine | Ingestion pipeline builds unified store | Ingestion report | OPEN | High | Unified ingestion missing | Build ingestion pipeline | Do not query fragmented sources manually | uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
57 | Phase 7 | Gate 7 | Intelligent Database | Intelligent DB | Stand up feature store query path | Need fast feature retrieval | Feature queries meet latency/contract requirements | Feature query benchmark | OPEN | Medium | Store not operational | Implement and benchmark feature queries | Do not read large flat files per request | uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
58 | Phase 7 | Gate 7 | Intelligent Database | Intelligent DB | Stand up label store query path | Need fast label retrieval | Label queries meet latency/contract requirements | Label query benchmark | OPEN | Medium | Store not operational | Implement and benchmark label queries | Do not duplicate label logic in clients | uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
59 | Phase 7 | Gate 7 | Intelligent Database | Intelligent DB | Stand up winner registry query path | Need runtime candidate access | Registry queries return approved truth consistently | Registry query benchmark | OPEN | High | Runtime service missing | Implement registry retrieval layer | Do not let clients parse raw registry files | uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
60 | Phase 7 | Gate 7 | Intelligent Database | Intelligent DB | Define retrieval contract for human and bot | Need same truth for both consumers | Single retrieval contract documented and tested | Retrieval contract | OPEN | High | Contract gap | Design one query contract for both users | Do not split truth models across clients | uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
61 | Phase 7 | Gate 7 | Intelligent Database | Intelligent DB | Implement retrieval ranking / similar-case lookup | Support intelligence-assisted decisions | Retrieval returns ranked relevant cases | Retrieval test report | OPEN | Medium | Retrieval logic missing | Implement ranking / vector or rule-based retrieval | Do not hardcode per-client lookup rules | uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
62 | Phase 7 | Gate 7 | Intelligent Database | Intelligent DB | Attach execution feedback to source intelligence records | Close intelligence loop | Executed outcomes map back to retrieved source records | Feedback linkage test | OPEN | High | Feedback link missing | Store retrieval IDs with execution outcomes | Do not lose source-to-outcome mapping | uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
63 | Phase 7 | Gate 7 | Intelligent Database | Intelligent DB | Set service SLOs and observability | Need production operability | Latency, error rate, and uptime metrics captured | Service observability report | OPEN | Medium | Service ops not defined | Add SLOs and monitoring | Do not call runtime ready without observability | uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
64 | Phase 8 | Deployment | Downstream / MT5 | Downstream Bot | Consume approved package manifest only | Prevent live path from reading raw exploratory truth | Bot config points to approved package only | Integration config check | OPEN | High | Approved-only path not enforced | Switch bot readers to approved packages | Do not read candidate/raw outputs directly | uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
65 | Phase 8 | Deployment | Downstream / MT5 | Downstream Bot | Map approved strategy package to executable signal model | Turn approved truth into live decision inputs | Signal package parsing test passes | Signal integration test | OPEN | High | Live adapter missing | Build package-to-signal adapter | Do not rebuild strategy truth inside bot | uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
66 | Phase 8 | Deployment | Downstream / MT5 | Downstream Bot | Implement market polling / event cadence | Need live trigger cadence | Polling/event loop meets design cadence | Runtime loop benchmark | OPEN | Medium | Live runtime not built | Implement polling/event loop | Do not overload live path with research cadence assumptions | uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
67 | Phase 8 | Deployment | Downstream / MT5 | Downstream Bot | Implement multi-winner scan and conflict resolution | Need controlled use of multiple approved candidates | Conflict rules are versioned and tested | Conflict resolution test | OPEN | Medium | Decision logic missing | Build signal ranking/conflict logic | Do not execute conflicting signals blindly | uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
68 | Phase 8 | Deployment | Downstream / MT5 | Downstream Bot | Implement position tracking and exposure guard | Need survivability controls | Position/exposure guard passes scenario tests | Risk control test | OPEN | High | Risk guard not operational | Implement position/exposure controls | Do not route orders without exposure guard | uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
69 | Phase 8 | Deployment | Downstream / MT5 | Downstream Bot | Implement micro-exit live control | Mandatory base layer must persist live | Micro-exit live handler tested end-to-end | Live exit test | OPEN | High | Live exit path missing | Build live micro-exit control | Do not downgrade live exits relative to research truth | uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
70 | Phase 8 | Deployment | Downstream / MT5 | MT5 Integration | Route approved signals to MT5 order layer | Need actual execution integration | Order route works in controlled environment | MT5 integration test | OPEN | High | MT5 route open | Build approved-signal order routing | Do not integrate with unapproved signals | uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
71 | Phase 8 | Deployment | Downstream / MT5 | MT5 Integration | Write execution outcomes back to central truth | Close research-to-live feedback loop | Execution log writes back with lineage IDs | Feedback write test | OPEN | High | Feedback loop open | Implement write-back path | Do not leave live outcomes outside central system | uploaded: Master Mapping Intelligent Data Base Production_v1_2_0.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
72 | Phase 9 | Ops Closure | Operations | Ops | Run weekly relabel / rerank loop | Keep intelligence current | Weekly refresh pipeline runs on schedule | Weekly refresh log | OPEN | Medium | Ops loop not operational | Implement weekly relabel/rerank | Do not freeze winners indefinitely | uploaded: PROJECT_PROGRESSION_CHECKLIST.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
73 | Phase 9 | Ops Closure | Operations | Ops | Refresh winner registry on schedule | Need controlled promotion/demotion cadence | Registry refresh cadence documented and run | Registry refresh log | OPEN | Medium | Ops cadence missing | Automate weekly registry refresh | Do not update winners ad hoc only | uploaded: PROJECT_PROGRESSION_CHECKLIST.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
74 | Phase 9 | Ops Closure | Operations | Ops | Demote losers and stale candidates automatically | Need lifecycle hygiene | Demotion rules run and are auditable | Demotion audit log | OPEN | Medium | Demotion automation missing | Implement demotion logic | Do not keep stale/losing candidates active | uploaded: PROJECT_PROGRESSION_CHECKLIST.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
75 | Phase 9 | Ops Closure | Operations | Ops | Create disaster recovery runbook for data, execution, DB, and bot | Need production survivability | Runbook exists and recovery drill passes | DR runbook + drill evidence | OPEN | High | No DR runbook | Write and test DR procedures | Do not call production-ready without DR | uploaded: PROJECT_PROGRESSION_CHECKLIST.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
76 | Phase 9 | Ops Closure | Operations | Ops | Set alerting for execution failures, recovery failures, and stale data | Need operator visibility | Alerts trigger on defined failure conditions | Alert test report | OPEN | High | Alerting not operational | Implement alert rules and tests | Do not depend on manual tailing only | uploaded: PROJECT_PROGRESSION_CHECKLIST.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
77 | Phase 9 | Ops Closure | Operations | Ops | Track production KPIs (latency, fail rate, skipped resumes, approval lag, data freshness) | Need measurable operations | KPI dashboard or report exists | Ops KPI report | OPEN | Medium | KPI framework missing | Define and publish KPIs | Do not manage production by anecdotes | uploaded: PROJECT_PROGRESSION_CHECKLIST.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
78 | Phase 9 | Ops Closure | Operations | Ops | Create change control for strategy, data schema, runner, and DB contract updates | Need safe evolution | Change control policy exists and is used | Change control policy | OPEN | Medium | Governance incomplete | Implement change control workflow | Do not hot-swap critical components silently | uploaded: PROJECT_PROGRESSION_CHECKLIST.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
79 | Phase 9 | Ops Closure | Operations | Ops | Declare production readiness only when all critical gates are closed | Need objective production decision | Go-live checklist signed with evidence | Production readiness pack | OPEN | Critical | Many gates still open | Use gate-based readiness review | Do not declare production from partial success | uploaded: PROJECT_PROGRESSION_CHECKLIST.txt; repo: https://github.com/tiumbj/Bot_Data_Basese |  |  |  | 0 | 0 | 1 | 0
Note on J15: Editable status. Use only DONE, IN_PROGRESS, OPEN, BLOCKED, or NOT_STARTED.
Note on O15: Use plain text source references or URLs. Keep evidence lineage explicit.

## 04_CURRENT_PRIORITY
Current Most Important Task | Build / promote a truly resume-safe execution runner.
Layer | Research Evidence / Execution Evidence
Gate | Gate 4
Input Truth | truth gate decision + truth_gate_seed_manifest + canonical dataset + locked TF rules
Output Truth | standardized result pack + explicit failure reasons + recovery metrics + same-outdir resume success
Gap Closed | RC-EXEC-RESUME-001 and related execution governance gaps
Why This Is Next | Current blocker is execution truth and recovery truth. Speed/cluster scale is secondary until Gate 4 is closed.
Required Acceptance Test | run -> partial progress -> kill -> restart same outdir -> verify skip completed work + no duplicate results + correct progress + visible recovery metrics
Not Allowed | Do not treat wrapper/watchdog as final answer. Do not rewrite around Ray now. Do not use per-attempt outdir as promoted recovery model.
Decision Rule | If a task does not move one OPEN gate closer to CLOSED, do not start it.
Architecture Direction vs Current Priority
Accepted Architecture Direction | Parquet + Zstd, Polars Lazy scan_parquet(), Arrow/NumPy-friendly columnar path, custom Numba kernel, separated orchestration, Polars aggregation.
Future Options | Ray for distributed orchestration later; Optuna for adaptive search later.
Not Current Next Action | Do not replace current roadmap with HPC architecture work before Gate 4 closure.

## 05_ANTI_DEVIATION
Question AI Must Answer Before Any New Task | Required Answer Shape | Reason | Immediate Stop Conditions
What layer is this task in? | One of: Data / Evidence / Registry / Feature-Label / Intelligent DB / Downstream Bot / Ops | Stops cross-layer drift | STOP | Counting scripts/specs as production progress
What gate does this task move? | Gate 1..7 or Ops Closure | Prevents unrelated work | STOP | Opening full-universe execution before truth gate + seed manifest
What is the input truth? | Exact artifact(s) consumed | Avoids hidden assumptions | STOP | Promoting runner versions without runner class and gate purpose
What is the output truth? | Exact artifact(s) produced | Forces machine-readable deliverables | STOP | Confusing orchestration logs with execution truth outputs
What production gap closes? | One named open gap only or primary gap | Prevents vague progress claims | STOP | Treating architecture ideas as current gate closure
What is the allowed next step? | One concrete next step | Keeps work sequenced | STOP | Using wrapper/watchdog as the final execution answer
What is not allowed while doing this? | Explicit prohibitions | Guards against deviation | STOP | Declaring production from partial success only
Why does this move production forward? | One or two sentences tied to gate closure | Stops architecture distraction

## 06_HANDOFF_TEMPLATE
CURRENT PROJECT POSITION
- Phase:
- Current Gate:
- Current Layer:
- Runner Class:
- Current Allowed Sequence Step:
- Current Production Gap:
- Last Proven Reality:
- What is CLOSED:
- What is still OPEN:
- Exact Next Task:
- Why this task is next:
- Not Allowed:
- Required evidence after completion:
RULE:
If the next task does not move one OPEN gate closer to CLOSED, do not start it.
PRE-HANDOFF CHECKS
[ ] I updated 03_DETAILED_CHECKLIST statuses
[ ] I attached evidence artifact names or paths
[ ] I wrote the current blocker clearly
[ ] I wrote one exact next task only
[ ] I listed what is not allowed next

## 07_EVIDENCE_LOG
Date | Phase | Gate | Artifact Name | Artifact Path / Link | What It Proves | Pass/Fail | Notes
2026-03-27 | Phase 4 | Gate 4 | Controlled clean 12-job run baseline | local artifact | A clean outdir and controlled execution can finish 12/12 jobs; useful baseline but not sufficient alone for resume-safe closure | PASS | Use as baseline evidence, not full gate closure

## 08_SOURCE_REGISTER
Source Type | Name | Reference | How Used
Repo | Bot_Data_Basese | https://github.com/tiumbj/Bot_Data_Basese | Top-level source of repo structure and project artifacts
Uploaded file | PROJECT_PROGRESSION_CHECKLIST.txt | local upload | Primary progression and anti-deviation basis
Uploaded file | Master Mapping Intelligent Data Base Production_v1_2_0.txt | local upload | Production truth map, phases, gaps, sequence
Uploaded file | project conversation.txt | local upload | Operational context and current position
User-provided analysis | Gemini HPC analysis | in-chat user text | Accepted as architecture direction only, not current next action